## Methodology
Likelihood | 1 | 2 | 3 | 4 | 5 | Treatment Decision | Meaning
| Rare | Unlikely | Possible | Likely | Almost Certain | Mitigate | Reduce the risk with controls | Residual Risk
[6 empty] | Accept | Keep the risk with formal acceptance
[6 empty] | Transfer | Shift part of the risk to a third party
[6 empty] | Avoid | Stop the risky activity
Impact | 1 | 2 | 3 | 4 | 5
| Negligible | Minor | Moderate | Major | Severe
Risk Score = Likelihood × Impact | 1_5 | 6_10 | 11_15 | 16_25
| Low | Medium | High | Critical
This risk assessment is based on a qualitative methodology using likelihood and impact scores from 1 to 5. Risks are evaluated in relation to TechNova Solutions’ SaaS environment, customer data processing activities, cloud infrastructure, and internal administrative access. Risk ratings are used to support prioritization and treatment planning.
Note on L2: Pc: Residual risk represents the remaining level of risk after existing or planned controls are considered.

## Risk Register
Risk ID | Asset / Process | Threat | Vulnerability | Risk Statement | Likelihood | Impact | Inherent Risk Score | Risk Rating | Existing Controls | Residual Risk | Risk Owner | Treatment Decision | Comments | Because of [vulnerability], [threat] could affect [asset/process], resulting in [business impact].
Unique ID | Related asset or business process | Source of risk | Weakness that could be exploited | Full risk description | 1–5 | 1–5 | Likelihood × Impact | Low / Medium / High / Critical | Current protections already in place | Remaining risk after controls | Person/role responsible | Mitigate / Accept / Transfer / Avoid | Extra notes
R-001 | Production Database | Unauthorized access | Excessive privileges / weak access governance | Because database access is not formally reviewed on a scheduled basis, unauthorized or excessive access could affect the production database, resulting in exposure or alteration of customer data. | 3 | 5 | 15 | High | Limited admin access, passwords in place | High | CTO | Mitigate | Needs formal access review and least privilege enforcement
R-002 | Cloud Admin Console | Account takeover | MFA not enforced for all privileged users | Because multi-factor authentication is not enforced for all privileged accounts, account takeover could affect the cloud administration environment, resulting in unauthorized changes, outage, or broader compromise. | 3 | 5 | 15 | High | Password authentication | High | CTO | Mitigate | Priority item
R-003 | Employee Laptops | Phishing / malware | Limited endpoint hardening and awareness | Because employee endpoints may not be consistently hardened and users may be exposed to phishing attempts, malware or credential theft could affect employee laptops, resulting in unauthorized access to business or production systems. | 4 | 4 | 16 | Critical | Basic antivirus, company laptops | High | Operations Lead | Mitigate | Awareness and endpoint controls needed
R-004 | Web Application | Application attack | Incomplete secure SDLC practices | Because secure development practices are not yet fully formalized, web application vulnerabilities could affect the customer-facing platform, resulting in data exposure, service disruption, or reputational damage. | 3 | 4 | 12 | High | Informal code review, developer testing | Medium/High | Engineering Lead | Mitigate | Add secure code review and remediation workflow
R-005 | Backend API / Services | Unauthorized API abuse / injection | Weak validation and incomplete monitoring | Because backend input validation and monitoring may be inconsistent, API abuse or malicious requests could affect application services, resulting in data manipulation, service degradation, or unauthorized actions. | 3 | 4 | 12 | High | Authentication logic, developer checks | Medium/High | Engineering Lead | Mitigate | Needs input validation and logging improvements
R-006 | Backup Storage | Recovery failure | Restore tests not documented or routine | Because backup restoration is not tested on a formal schedule, a failure in recovery could affect business continuity after a security incident or operational outage. | 2 | 5 | 10 | Medium | Backups exist | Medium | Operations Lead | Mitigate | Restore testing required
R-007 | Logging and Monitoring | Late detection of incident | Incomplete log coverage and review | Because logging coverage and review activities are limited, security incidents may not be detected or investigated in a timely manner, resulting in prolonged exposure or delayed response. | 3 | 4 | 12 | High | Basic cloud logs and app logs | Medium/High | Operations Lead | Mitigate | Centralized review process needed
R-008 | Source Code Repository | Unauthorized code changes / leakage | Weak branch protections or access restrictions | Because repository governance may not be fully controlled, unauthorized code changes or source code leakage could affect the integrity and security of the SaaS platform. | 3 | 4 | 12 | High | Developer accounts, private repository | Medium | Engineering Lead | Mitigate | Add branch protection and access review
R-009 | Customer Support Admin Panel | Excessive internal access | Weak role-based access enforcement | Because support privileges may not be tightly restricted, excessive access could affect customer-facing records, resulting in unauthorized viewing or misuse of customer information. | 3 | 4 | 12 | High | Support accounts exist | Medium/High | Support Lead | Mitigate | Define RBAC and review support permissions
R-010 | Security Governance / Policies | Inconsistent security practices | Security procedures not yet fully documented | Because security policies and procedures are still immature, inconsistent security practices could affect multiple systems and processes, resulting in control gaps and reduced audit readiness. | 4 | 3 | 12 | High | Partial informal practices | Medium | Management / Junior GRC Analyst | Mitigate | Policy pack needed

## Risk Matrix
Impact \ Likelihood | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25 | Critical
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15 | High
2 | 2 | 4 | 6 | 8 | 10 | Medium
1 | 1 | 2 | 3 | 4 | 5 | Low