## Feuil1
Treatment ID | Related Risk ID | Risk Description | Selected Treatment | Planned Control / Action | Control Reference | Priority | Owner | Target Date | Status | Expected Residual Risk | Success Measure | Notes
Unique action ID | Link to the risk register | Short description of the risk | Mitigate / Accept / Transfer / Avoid | What will be done | ISO / NIST reference | High / Medium / Low | Responsible role | Planned completion date | Planned / In Progress / Completed | Risk level after treatment | How you know it worked | Extra implementation notes
T-001 | R-001 | Unauthorized or excessive access to production database | Mitigate | Implement least privilege access model and perform quarterly database access reviews | ISO 27001 Annex A - Access Control / NIST AC | High | CTO | 2026-05-15 | Planned | Medium | Access review completed and unnecessary privileges removed | Formal owner approval required | Critical / High risks → High priority
T-002 | R-002 | Account takeover of cloud admin console | Mitigate | Enforce MFA for all privileged accounts and review all admin accounts | ISO 27001 Annex A - Identity and Authentication / NIST IA | High | CTO | 2026-04-30 | In Progress | Low | 100% of privileged accounts protected with MFA | Priority remediation | Medium risks → Medium priority
T-003 | R-003 | Phishing or malware affecting employee laptops | Mitigate | Strengthen endpoint protection and launch basic security awareness training | ISO 27001 Annex A - Endpoint Security / NIST AT, SI | High | Operations Lead | 2026-05-20 | Planned | Medium | Endpoint protection active and awareness session completed | Include phishing awareness | Low risks → Low priority
T-004 | R-004 | Web application vulnerabilities due to weak secure SDLC | Mitigate | Introduce formal secure code review checklist and vulnerability remediation tracking | ISO 27001 Annex A - Secure Development / NIST SA, SI | High | Engineering Lead | 2026-06-01 | Planned | Medium | Code review checklist used for all releases | Start with critical modules
T-005 | R-005 | API abuse or injection through weak validation | Mitigate | Standardize input validation, improve API error handling, and log suspicious requests | ISO 27001 Annex A - Application Security / NIST SI, AU | High | Engineering Lead | 2026-06-10 | Planned | Medium | Validation controls documented and suspicious requests logged | Coordinate with dev team
T-006 | R-006 | Backup restoration failure | Mitigate | Establish quarterly restore testing and document backup recovery procedure | ISO 27001 Annex A - Backup / NIST CP | Medium | Operations Lead | 2026-05-25 | Planned | Low | Restore test completed successfully and documented | Keep test evidence
T-007 | R-007 | Delayed detection due to incomplete logging and monitoring | Mitigate | Define minimum logging requirements and perform weekly log review for critical systems | ISO 27001 Annex A - Logging and Monitoring / NIST AU | High | Operations Lead | 2026-05-30 | Planned | Medium | Critical systems produce logs and weekly review evidence exists | Start with admin, app, and DB logs
T-008 | R-008 | Unauthorized code changes or source code leakage | Mitigate | Enable branch protection, restrict repository access, and review privileged developers | ISO 27001 Annex A - Change Management / NIST CM, AC | Medium | Engineering Lead | 2026-05-18 | Planned | Low | Protected branches enabled and access list reviewed | Apply to production repositories first
T-009 | R-009 | Excessive support access to customer information | Mitigate | Define role-based access model and review support permissions quarterly | ISO 27001 Annex A - Access Control / NIST AC | High | Support Lead | 2026-05-22 | Planned | Medium | Support roles documented and permissions aligned to job need | Management approval needed
T-010 | R-010 | Inconsistent security practices due to immature governance | Mitigate | Approve baseline security policies and define policy review cadence | ISO 27001 Annex A - Information Security Policies / NIST GV | High | Management / Junior GRC Analyst | 2026-05-12 | In Progress | Medium | Policy pack approved and review schedule defined | Foundation for audit readiness